## 0_Instructions
Department Release & Sigon Management System
Workbook Overview
Sheet Name | Purpose
0_Instructions | This page — describes each sheet and how to use the workbook
1_Release Register | Master list of all Releases (type, year, status, cross-year flag). This is the key reference for all other sheets.
2_eBCI Requests | Tracks eBCI approval form status for every Java Release (Java Releases only)
3_Env Deployment Schedule | Records the organisation-mandated UT/UA/OT/PR deployment & Sigon dates for each Release
4_MF Access Requests | Tracks Mainframe access-permission requests for UA/OT/PR deployments (≥15-day advance submission; ≥3 business-day advance verification)
5_Sigon Assignments | Personnel assignments for each Sigon (Mainframe + Java TDAP/TDWS)
6_Sigon Execution Log | Actual Sigon execution results, issues found, and follow-up actions
7_Staff Directory | Department roster (Mainframe team + Java team) — used as dropdown source in other sheets
8_Leave Calendar | Staff leave records — reference when arranging Sigon assignments
9_Dashboard | Summary view: Release progress, pending items, and risk alerts
Status Colour Legend
✅ Completed / Approved
⏳ In Progress / Pending / To-Do
❌ Incomplete / Rejected / Overdue
— Not Applicable / N/A
💡 How to Use
1. Start in [1_Release Register] — enter each Release. The Release ID is the linking key used by all other sheets.
2. If the Release includes Java changes, go to [2_eBCI Requests] and log the approval form submission.
3. Go to [3_Env Deployment Schedule] and enter the organisation-confirmed UT/UA/OT/PR deployment dates.
4. If the Release includes Mainframe changes, track permission requests in [4_MF Access Requests].
5. Arrange Sigon personnel in [5_Sigon Assignments], cross-referencing [8_Leave Calendar] for conflicts.
6. On or after each Sigon, record the outcome in [6_Sigon Execution Log].
7. Use [9_Dashboard] for an at-a-glance progress and risk summary.

## 1_Release Register
Release Register — Master Record for All Releases
Note: Suggested Release ID format: [Year]-[Type], e.g. 2026-Spring. The Mainframe/Java flags drive the downstream workflow.
Release ID | Release Name | Year | Release Type | Mainframe Changes? | Java Changes? | Java Product(s) | Dev Start Date | Planned PR Go-Live | Cross-Year? | Overall Status
2026-January | 2026 January Release | 2026 | January | Yes | Yes | TDAP | 2025-10-01 | 2026-01-15 | Yes | In Progress
2026-February | 2026 February Release | 2026 | February | No | Yes | TDWS | 2025-11-01 | 2026-02-20 | Yes | In Progress
2026-Spring | 2026 Spring Release | 2026 | Spring | Yes | Yes | TDAP, TDWS | 2026-01-15 | 2026-05-30 | No | Not Started
2026-Fall | 2026 Fall Release | 2026 | Fall | Yes | No | — | 2026-06-01 | 2026-10-15 | No | Not Started

## 2_eBCI Requests
eBCI Approval Request Log — Java Releases Only
Note: Every Java Release requires an approved eBCI form before the development cycle begins. Track submission and approval status here.
Release ID | Java Product | Submitted By | Submission Date | Request No. | Status | Approval / Rejection Date | Approver | Notes
2026-January | TDAP | (Sample) David Chen | 2025-09-15 | EBCI-2025-1001 | Approved | 2025-09-25 | (Sample) Manager A
2026-February | TDWS | (Sample) Alice Wong | 2025-10-10 | EBCI-2025-1015 | Approved | 2025-10-20 | (Sample) Manager A
2026-Spring | TDAP | (Sample) David Chen |  |  | To Submit |  |  | Waiting for dev plan confirmation
2026-Spring | TDWS | (Sample) Alice Wong |  |  | To Submit

## 3_Env Deployment Schedule
Environment Deployment / Sigon Schedule
Note: Dates are set by the organisation. The department must comply. Sigon = post-deployment verification. Update the status column after each Sigon.
Release ID | Change Scope | UT Environment |  |  | UA Environment |  |  | OT Environment |  |  | PR Environment (Go-Live)
|  | Sigon Date | Sigon Status | Notes | Sigon Date | Sigon Status | Notes | Sigon Date | Sigon Status | Notes | Sigon Date | Sigon Status | Notes
2026-January | Java (TDAP) | 2025-10-15 | Completed |  | 2025-11-15 | Completed |  | 2025-12-15 | Completed |  | 2026-01-15 | Pending
2026-February | Java (TDWS) | 2025-11-15 | Completed |  | 2025-12-15 | In Progress |  |  | Not Started |  | 2026-02-20 | Not Started
2026-Spring | Mainframe + Java |  | Not Started |  |  | Not Started |  |  | Not Started |  | 2026-05-30 | Not Started
2026-Fall | Mainframe |  | Not Started |  |  | Not Started |  |  | Not Started |  | 2026-10-15 | Not Started

## 4_MF Access Requests
Mainframe Access Permission Request Tracker
Note: Mainframe access for UA/OT/PR must be requested ≥15 calendar days before Sigon. Approval must be verified ≥3 business days before Sigon. Overdue cells turn red automatically.
Release ID | Environment | Sigon Date | Requestor ID | Requestor Name | Request Submission Date | Submission Deadline (Sigon−15 days) | Request Status | Verification Date | Verification Deadline (Sigon−3 bus. days) | Verification Result | Notes
2026-January | UA | 2025-11-15 | MF001 | (Sample) John Smith | 2025-10-25 | 45961 | Approved | 2025-11-12 | 45973 | Confirmed
2026-January | OT | 2025-12-15 | MF001 | (Sample) John Smith | 2025-11-25 | 45991 | Approved | 2025-12-10 | 46001 | Confirmed
2026-January | PR | 2026-01-15 | MF002 | (Sample) Mary Lee | 2025-12-25 | 46022 | Under Review |  | 46034 | Pending
2026-Spring | UA |  | MF001 | (Sample) John Smith |  |  | Not Requested

## 5_Sigon Assignments
Sigon Execution Personnel Assignments
Note: Assign personnel for each Sigon. Mainframe and Java (TDAP / TDWS) are assigned separately. If resource-constrained, one person may cover both Java products.
Release ID | Environment | Sigon Date | Mainframe Assignee | TDAP Assignee | TDWS Assignee | Resource Conflict? | Confirmation Status | Notes
2026-January | UT | 2025-10-15 | — | (Sample) David Chen | — | OK | Confirmed | TDAP only
2026-January | UA | 2025-11-15 | (Sample) John Smith | (Sample) David Chen | — | OK | Confirmed
2026-January | OT | 2025-12-15 | (Sample) John Smith | (Sample) David Chen | — | OK | Confirmed
2026-January | PR | 2026-01-15 | (Sample) Mary Lee | (Sample) David Chen | — | OK | Pending | MF covered by Mary
2026-February | UA | 2025-12-15 | — | — | (Sample) Alice Wong | OK | Confirmed | TDWS only

## 6_Sigon Execution Log
Sigon Execution Results Log
Note: Complete this sheet on or after each Sigon. Record the actual outcome, issues found, and any follow-up actions required.
Release ID | Environment | Sigon Date | Actual Start | Actual End | Result | Issues Found (#) | Issue Description / JIRA Tickets | Follow-up Actions | Logged By
2026-January | UT | 2025-10-15 | 09:00 | 11:30 | Success | 0 | None | Proceed to UA prep | (Sample) David Chen
2026-January | UA | 2025-11-15 | 10:00 | 14:00 | Success | 2 | JIRA-1234, JIRA-1235 (resolved) | Proceed to OT | (Sample) John Smith
2026-January | OT | 2025-12-15 | 10:00 | 15:00 | Success | 1 | JIRA-1240 (resolved) | Prepare for PR go-live | (Sample) John Smith

## 8_Leave Calendar
Staff Leave Register
Note: Log all planned leave here so that Sigon assignment conflicts can be identified early.
Employee ID | Full Name | Leave Type | Start Date | End Date | Notes
JV001 | (Sample) David Chen | Annual Leave | 2026-02-10 | 2026-02-17 | Lunar New Year
MF001 | (Sample) John Smith | Sick Leave | 2026-03-05 | 2026-03-07

## 9_Dashboard
Release Management Dashboard
Auto-summary — sources: 1_Release Register / 2_eBCI Requests / 4_MF Access Requests. Click through to each sheet for details.
📊 Release Status Summary |  | 📝 eBCI Approval Status
Status | Count | Status | Count
Not Started | 2 | To Submit | 2
In Progress | 2 | Submitted | 0
In Testing | 0 | Under Review | 0
Live | 0 | Approved | 2
Cancelled | 0 | Rejected | 0
Total | 4
🔐 MF Access Request Status |  | ⚠️ Risk Alerts
Status | Count | Item | Count
Not Requested | 1 | MF requests overdue (not yet approved) | 1
Submitted | 0 | MF verifications overdue (not confirmed) | 1
Under Review | 1 | Sigon assignments pending confirmation | 1
Approved | 2 | Sigon resource conflicts detected | 0
Rejected | 0
📅 Upcoming Sigons (refer to 3_Env Deployment Schedule and 5_Sigon Assignments for details)
Sigon count in the next 30 days (UT + UA + OT + PR combined) |  |  | 0

## 7_Staff Directory
Department Staff Directory
Employee ID | Full Name | Team | Product / Role | Notes
MF001 | (Sample) John Smith | Mainframe | Mainframe Dev | Has permanent UT access
MF002 | (Sample) Mary Lee | Mainframe | Mainframe Dev
JV001 | (Sample) David Chen | Java | TDAP
JV002 | (Sample) Alice Wong | Java | TDWS
JV003 | (Sample) Bob Martin | Java | TDAP / TDWS | Can cover both products